## Sheet1
Sr- No- | Tender Number | A.A. Number | AA GR Date | Received From Department | Date of Proposal Received | Total Amount of Proposed Item | Tender Sale Period Start Date | Sale Period End Date | Pre Bid Meeting Date | Pre Bid Uploaded Date | Extension -1 till date | Extension -2 till date | Technical Bid opening Date | Financial Bid opening Date | Current Status | Category | Remarks / Current Status of File
1 | E-241 | 13 | 14/02/2025 | PHD | 14/02/2025 | 55910000 | 2025-04-11 | 19/12/2025 | 2025-12-11 |  | 29/12/2025 | 2026-07-01 | 19/01/2026 |  | Technical Bid | Tender Under Process | • Shortfall letter sent to respective bidders & last date of shortfall submission 11.03.2026 • Shortfall Under Evaluation
2 | E-242 | 127 | 18/06/2025 | PHD | 23/07/2025 | 60615720 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | • Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
3 | E-242 | 261 | 2025-11-08 | DMER | 13/08/25 | 88732226 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | •Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
4 | E-242 | 139 (R) | 29/08/2025 | PHD | 29/08/2025 | 6769712 | 2025-04-11 | 20/02/2026 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | •Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
5 | E-242 | 191 | 2025-06-10 | PHD | 17/10/2025 | 6280020 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | • Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
6 | E-242 | 14264-70 | 15/07/2025 | PHD | 22/07/2025 | 2501200 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | •Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
7 | E-242 | 13 | 14/02/2025 | PHD | 14/02/2025 | 66548212 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
8 | E-242 | SBTC 807 | 2025-10-07 | SBTC | 18/8/2025 | 11014500 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | • Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
9 | E-242 | 180 | 2025-01-10 | PHD | 13/10/2025 | 300,05,317 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 23/03/2026 |  |  |  | Ext-1 | Tender Under Process | • Technical bid will be opened on Date 06.04.2026 • II Extension till date 23.03.2026 to 02.04.2026
10 | E-243 | 130 | 18/06/2025 | PHD | 14/02/2025 | 254423044 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 2026-04-03 | 2026-12-03 | 17/03/2026 |  | Technical Bid | Tender Under Process | • Technical bid opened on 17.03.2025 • Technical Evaluation Under Process.
11 | E-243 | 261 | 2025-11-08 | DMER | 13/08/25 | 1815352 | 2025-04-11 | 26/11/2025 | 2025-12-11 |  | 2026-04-03 | 2026-12-03 | 17/03/2026 |  | Technical Bid | Tender Under Process | • Technical bid opened on 17.03.2025 • Technical Evaluation Under Process.
12 | E-243 | 139 (R) | 29/08/2025 | PHD | 29/08/2025 | 630000 | 2025-04-11 | 23/02/2026 | 2025-12-11 |  | 2026-04-03 | 2026-12-03 | 17/03/2026 |  | Technical Bid | Tender Under Process | • Technical bid opened on 17.03.2025 • Technical Evaluation Under Process.
13 | E-253 | 139 | 2025-12-06 | PHD | 19/06/2025 | 159584000 | 29/01/2026 | 18/02/2026 | 2026-09-02 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender under sale period • Pre Bid Queries sent to department on 04.03.2026 • Corrigendum IV 18.03.2026 to 30.03.2026 • Corrigendum V 30.03.2026 to 09.04.2026
14 | E-253 | 180 | 2025-01-10 | PHD | 13/10/2025 | 10100307 | 29/01/2026 | 18/02/2026 | 2026-09-02 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender under sale period • Pre Bid Queries sent to department on 04.03.2026 • Corrigendum IV 18.03.2026 to 30.03.2026 • Corrigendum V 30.03.2026 to 09.04.2026
15 | E-253 | 261 | 2025-11-08 | DMER | 13/08/25 | 7776164 | 29/01/2026 | 18/02/2026 | 2026-09-02 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender under sale period • Pre Bid Queries sent to department on 04.03.2026 • Corrigendum IV 18.03.2026 to 30.03.2026 • Corrigendum V 30.03.2026 to 09.04.2026
16 | E-253 | 139 (R) | 29/08/2025 | PHD | 29/08/2025 | 84,35,750 | 29/01/2026 | 18/02/2026 | 2026-09-02 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender under sale period • Pre Bid Queries sent to department on 04.03.2026 • Corrigendum IV 18.03.2026 to 30.03.2026 • Corrigendum V 30.03.2026 to 09.04.2026
17 | E-253 | 127 | 18/06/2025 | PHD | 23/07/2025 | 334387500 | 29/01/2026 | 18/02/2026 | 2026-09-02 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender under sale period • Pre Bid Queries sent to department on 04.03.2026 • Corrigendum IV 18.03.2026 to 30.03.2026 • Corrigendum V 30.03.2026 to 09.04.2026
18 | E-254 | 1180-88 | 2026-08-01 | PHD | 14/01/2026 | 99999997 | 29/01/2026 | 18/02/2026 | 2026-04-02 |  | 2026-09-03 |  |  |  | Ext-1 | Tender Under Process | • Tender under First Extension upto-09.03.2026
19 | E-255 | 44 | 2026-05-01 | ICDS | 2026-05-01 | 165936000 | 13/02/2026 | 2026-09-03 | 20/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • sale period till date 01.04.2026 • Pre-bid compliance upload on Date 25.03.2026
20 | E-266 | 139 | 2025-12-06 | PHD |  | 104050856 | 26/02/2026 | 20/03/2026 | 2026-05-03 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender Under sale period upto 01.04.2026 • Prebid queries letter sent to dept on dt. 18.03.2026
21 | E-266 | 128 | 18/06/2025 | PHD |  | 455027392 | 26/02/2026 | 20/03/2026 | 2026-05-03 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender Under sale period upto 01.04.2026 • Prebid queries letter sent to dept on dt. 18.03.2026
22 | E-266 | NHM 53498-504 | 2025-04-08 | NHM |  | 505032067 | 26/02/2026 | 20/03/2026 | 2026-05-03 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender Under sale period upto 01.04.2026 • Prebid queries letter sent to dept on dt. 18.03.2026, Remider Letter sent on 27.03.2026
23 | E-267 | 0226/25 | 2026-11-02 | DMER | 2026-11-02 | 154266607 | 27/02/2026 | 23/03/2026 | 2026-09-03 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender Under Sale Period On 27.02.2026 to 23.03.20256 • Corrigendum I 23.03.2026 to 02.04.2026 • Prebid quiry Letter send on 23.03.2026.
24 | E-268 | 0226/25 | 2026-11-02 | DMER | 2026-11-02 | 648603280 | 2026-10-03 | 2026-02-04 | 18/03/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Sale Period till date 06.04.2026 • Pre-bid compliance upload on Date 25.03.2026"
25 | RT-218 | 139 | 2025-12-06 | PHD | 19/06/2025 | 242801875 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
26 | RT-218 | 139 (R) | 29/08/2025 | PHD | 29/08/2025 | 12455609 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
27 | RT-218 | 261 | 2025-11-08 | DMER | 13/08/25 | 51682980 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
28 | RT-218 | 127 | 18/06/2025 | PHD | 23/07/2025 | 97003485 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
29 | RT-218 | 14264-70 | 15/07/2025 | PHD | 22/07/2025 | 1926600 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
30 | RT-218 | 191 | 2025-06-10 | PHD | 17/10/2025 | 4250400 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
31 | RT-218 | 13 | 14/02/2025 | PHD | 14/02/2025 | 55544925 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
32 | RT-218 | 180 | 2025-01-10 | PHD | 13/10/2025 | 804000 | 16/02/2026 | 18/03/2026 | 25/02/2026 | [5 empty] | Pre Bid Stage | Tender Under Process | • Prebid queries letter sent to dept on dt. 27.02.2026 • Pre bid Compliance not received from concerned department • 1 st Corrigendum till dt. 30.03.2026
33 | RT-238 | 139 (R) | 29/08/2025 | PHD | 29/08/2025 | 271400 | 2025-05-12 | 20/01/2026 | 2025-11-12 |  | 29/01/2026 | 2026-06-02 | 2026-10-02 | 2026-12-03 | Financial Bid Stage | Tender Under Process | • TAC done on Date:23.03.2026 • Negotiation Letter sent on Dt.24.03.2026
34 | RT-238 | 87460-465 | 15/10/2025 | NHM | 17/10/2025 | 413417253 | 2025-05-12 | 2026-08-01 | 2025-11-12 |  | 29/01/2026 | 2026-06-02 | 2026-10-02 | 2026-12-03 | Financial Bid Stage | Tender Under Process | • TAC done on Date:23.03.2026 • Negotiation Letter sent on Dt.24.03.2026
35 | RT-238 | 14264-70 | 15/07/2025 | PHD | 22/07/2025 | 28,22,300 | 2025-05-12 | 2026-08-01 | 2025-11-12 |  | 29/01/2026 | 2026-06-02 | 2026-10-02 | 2026-12-03 | Financial Bid Stage | Tender Under Process | • TAC done on Date:23.03.2026 • Negotiation Letter sent on Dt.24.03.2026
36 | RT-238 | 191 | 2025-06-10 | PHD | 17/10/2025 | 5648896 | 2025-05-12 | 2026-08-01 | 2025-11-12 |  | 29/01/2026 | 2026-06-02 | 2026-10-02 | 2026-12-03 | Financial Bid Stage | Tender Under Process | • TAC done on Date:23.03.2026 • Negotiation Letter sent on Dt.24.03.2026
37 | RT-239 | 87460-465 | 15/10/2025 | NHM | 17/10/2025 | 23070622 | 2026-02-03 | 30/03/2026 | 2026-10-03 | [5 empty] | Pre Bid Stage | Tender Under Process | • Tender Under First Extension till date 08.04.2026
38 | RT-240. | 545-549 | 2025-08-12 | PHD | 2025-10-12 | 4729478 | 2026-04-03 | 25/03/2026 | 2026-11-03 |  | 2026-07-04 |  |  |  | Ext-1 | Tender Under Process | • Tender Under First Extension upto 07.04.2026
39 | RT-240. | 87460-465 | 15/10/2025 | PHD | 16/10/2025 | 67651100 | 2026-04-03 | 25/03/2026 | 2026-11-03 |  | 2026-07-04 |  |  |  | Ext-1 | Tender Under Process | • Tender Under First Extension upto 07.04.2026
40 | E-20 |  | 24/03/2023 | PHD | 2023-07-10 | 13783108 | 2023-10-11 | 2023-01-12 | 16/11/2023 |  | 2023-11-12 | 19/12/2023 | 19/12/2023 | 19/03/2024 | L1 Finalised | PO Awaited | • PO Issued on 07.08.2025 (Rs.118616892)
41 | E-204/207 | 19 | 17/02/2025 | PHD | 2025-12-03 | 34001807 | [8 empty] | L1 Finalised | PO Awaited | • Note put up for Purchase order on 20-03-2025
42 | E-204/207 | 141873-78 | 24/02/2026 | NHM | 24/02/2026 | 86360139 | [8 empty] | L1 Finalised | PO Awaited | • Letter Sent to Concerned dpt. for revised Consignee on 05.03.2026
43 | E-215 | 13 | 14/02/2025 | DHS | 14/02/2025 | 366347450 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | • Order Issused for 6 Items for Prama 139,(Value 11,22,33,032)on 27.02.2026
44 | E-215 | 86 | 14/02/205 | DHS | 19/03/2025 | 31173388 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | • TAC On Date 05.02.2026 • L1Finalised item 32 worth Amt 19,64,88,400/- • 20 Items Zero Bidder Value Rs. 5,36,82,500/- • L1 rate higher than AA rate 15 items worth rs. 11,61,76,550/- • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
45 | E-215 | 39 | 31/07/2025 | DHS | 2025-12-08 | 174399587 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | • L1 Finalised item 8 worth Amt 1,85,11,462/- • 7 Items Zero Bidder Value Rs. 1,26,61926/- • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
46 | E-215 | 139(inf) | 14/02/2025 | PHD | 18/02/2025 | 178897351 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | • L1 Finalised item 21 worth Amt 12,60,20,262 • 2 Items Zero bidder Value Rs. 64,83,970 • L1 rate higher than AA rate 8 items worth rs. 4,18,95,355/- • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
47 | E-215 | 261 | 2025-11-08 | DMER | 13/08/25 | 44550879 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | • Price bid opened on 05.02.2026, • TAC on 05.02.2026 • Letter Issued to Dpt. on 11.02.2026 about consignee & Funds. • L1Finalised item 13 worth Amt 7,45,86,463 • Negotiation letter send to respective bidder last date of submission 13.02.2026 • L1 Rate Matching Letter Sent to respective bidder last date of submission 20.02.2026 • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
48 | E-215 | 125 | 13/06/2025 | PHD | 23/07/2025 | 167370000 | [8 empty] | L1 Finalised | PO Awaited | • Price bid opened on 05.02.2026, • TAC on 05.02.2026 • Letter Issued to Dpt. on 11.02.2026 about consignee & Funds. L1Finalised item 61 worth Amt 21,27,13,970.05 • Negotiation letter send to respective bidder last date of submission 13.02.2026 • 20 Items PO Issued on date: 20.02.2026 (Value 8,38,13,042) • 19 Items PO Issued on date: 27.02.2026 (Value 4,37,48,038) • 9 Items PO Issued on date: 05.03.2026 (Value 2,96,03,895) • 14 Items PO Issued on date: 11.03.2026 (Value 4,87,26,768)
49 | E-215 | Owt No.58719-724 | 20/08/2025 | PHD | 2025-05-12 | 7,69,78,487 | [8 empty] | L1 Finalised | PO Awaited | • TAC On Date 05.02.2026 • L1Finalised item 26 worth Amt 54,40,50,885 • Negotiation letter send to respective bidder last date of submission 13.02.2026 • L1 Rate Matching Letter Sent to respective bidder last date of submission 20.02.2026 • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
50 | E-215 | Owt No.5716-22 | 20/11/2025 | PHD | 25/11/2025 | 8802320 | [8 empty] | L1 Finalised | PO Awaited | • L1Finalised item 09 worth Amt 32,40,49,171/- • L1 rate higher than AA rate 01 items worth rs. 64,37,866/- • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
51 | E-215 | 127 | 18/06/2025 | PHD | 23/07/2025 | 1341498585 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | • TAC On Date 05.02.2026 • L1Finalised item 14 worth Amt 1,26,68,174.78 • Negotiation letter send to respective bidder last date of submission 13.02.2026 • L1 Rate Matching Letter Sent to respective bidder last date of submission 20.02.2026 • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
52 | E-215 | 130 | 18/06/2025 | PHD | 14/02/2025 | 326437866 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | 1. L1Finalised item 226 worth Amt Rs. 85,28,57,854/- Awaited for consignee 2. L1 rate higher than AA rate 70 items worth rs.36,51,59,744/- 3. Zero Response item 215 worth Rs. 50,52,65,778/- 4. Awaited for consignees (Letter sent to dept for consignee on 11.02.2026 & 25.02.2026) 5.Consignee Received on dt.10.032026; PO note put up on 17.03.2026 6. Consignee Received on dt. 16.03.2026 & 20.03.2026
53 | E-215 | 134 | 2025-12-06 | DHS | 2025-12-06 | 98155527 | 2025-04-09 | 29/09/2025 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-05-02 | L1 Finalised | PO Awaited | 1. L1Finalised item 158 worth Amt Rs. 1,23,50,971/- 2. L1 rate higher than AA rate 44 items worth rs. 1,61,40,371/- 3. Zero Response item 119 worth Rs. 56,27,140/- 4. Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
54 | E-215 | 139 | 2025-12-06 | PHD | 19/06/2025 | 2123417232 | 2025-04-09 | 2025-06-11 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-04-02 | L1 Finalised | PO Awaited | • TAC On Date 05.02.2026 • Consignee recevied on 20.03.2026; PO note put up 23.03.2026 1 item No Response worth Amnt Rs. 51,09,480/-
55 | E-215 | 139 (R) | 29/08/2025 | PHD | 29/08/2025 | 57579401 | 2025-04-09 | 2025-06-11 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-04-02 | L1 Finalised | PO Awaited | • TAC On Date 05.02.2026 • 97 items Approved worth Rs.47,52,29,582/- • 45 items No Response Rs.8,51,74,827/- • 38 Items items L1 Rate is higher than AA Rate Rs.22,77,70,680/- • Awaited for fund and consignees (Letter sent to dept for fund and consignee on 11.02.2026 & 25.02.2026)
56 | E-215 | 19 | 17/02/2025 | PHD | 2025-12-03 | 449472 | 2025-04-09 | 2025-06-11 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-04-02 | L1 Finalised | PO Awaited | 24 items in E-249 • 23 items got No response Rs.4,53,22,676/- • 1 item will be put up in next TAC (after Negotiation)
57 | E-215 | 125 | 13/06/2025 | PHD | 23/07/2025 | 938100344 | 2025-04-09 | 2025-06-11 | 2025-11-09 |  | 17/11/2025 | 26/11/2025 | 27/11/2025 | 2025-04-02 | L1 Finalised | PO Awaited | 07 items in E- 249 • 06 items got No response Rs.1,46,76,939/- ; Retender note put up 13.03.2026 • 01 item Approved in TAC date-28.02.2026 Rs.3,81,30,032/- • Letter sent to dept for consignee on dt. 05.03.2026,12.03.2026
58 | E-220 | 13 | 14/02/2025 | DHS | 14/02/2025 | 8882500 | 30/09/2025 | 2025-06-11 | 2025-08-10 |  | 24/10/2025 | 2025-06-11 | 17/11/2025 | 2026-07-01 | L1 Finalised | PO Awaited | 07 items in E- 248 • 05 items got No response Rs.1,43,16,899/-; Retender note put up 13.03.2026 • 01 item L1 Rate is higher than AA Rate TAC Date-28.02.2025 ;Rs. 6,41,969/- • 01 item Approved TAC on Dt.28.02.2026 Rs. 23919301 • Letter sent to dept for consignee on dt. 05.03.2026,12.03.2026
59 | E-248 | Owt No.58719-724 | 20/08/2025 | Urban Health | 2025-05-12 | 23919301 | 2025-08-12 | 31/12/2025 | 15/12/2025 |  | 2026-09-01 | 20/01/2026 | 21/01/2026 | 23/02/2026 | L1 Finalised | PO Awaited | 16 Items in E-248 • 15 items got No response Rs.1,63,15,924/- • 01 item get response Rs.6,66,520/- ; but L1 Rate is higher than AA Rate, TAC Date-28.02.2026
60 | E-248 | 19 | 17/02/2025 | PHD | 2025-12-03 | 16539711 | 2025-08-12 | 31/12/2025 | 15/12/2025 |  | 2026-09-01 | 20/01/2026 | 21/01/2026 | 23/02/2026 | L1 Finalised | PO Awaited | No Response all 02 items ; Retender note put up 13.03.2026
61 | E-248 | 139 | 2025-12-06 | PHD | 19/06/2025 | 3300000 | 2025-08-12 | 31/12/2025 | 15/12/2025 |  | 2026-09-01 | 20/01/2026 | 21/01/2026 | 23/02/2026 | L1 Finalised | PO Awaited | • 3 items Mehru mehta Direct Purchase awaited for fund and consignee (Rs. 25,18,000/-) • 3 items HBPCL reserved awaited for fund and consignee (Rs. 22,90,500/-) • Letter sent to department regarding consignees on 06.03.2026
62 | E-249 | 19 | 17/02/2025 | PHD | 2025-12-03 | 48335367 | 2025-08-12 | 16/01/2026 | 15/12/2025 |  | 27/01/2026 | 2026-04-02 | 2026-05-02 | 23/02/2026 | L1 Finalised | PO Awaited | 5 Item HBPCL Reserved (Medicine) approved in TAC 23.09.2025 Awaited For Consignee letter to department Regarding Consignee on dt.18.03.2026
63 | E-249 | Owt No.58719-724 | 20/08/2025 | Urban Health | 2025-05-12 | 6,10,54,010 | 2025-08-12 | 16/01/2026 | 15/12/2025 |  | 27/01/2026 | 2026-04-02 | 2026-05-02 | 23/02/2026 | L1 Finalised | PO Awaited | • 03 items HBPCL/HAPL reserved Approved in TAC 20.02.2026 • awaited for consignee • Letter send to concerned department regarding revised consignee on dt.11.02.2026 & 05.03.2026,12.03.2026
64 | E-249 | Owt No.5716-22 | 20/11/2025 | PHD | 25/11/2025 | 1231035 | 2025-08-12 | 16/01/2026 | 15/12/2025 |  | 27/01/2026 | 2026-04-02 | 2026-05-02 | 23/02/2026 | L1 Finalised | PO Awaited | • 20 items for repeat order w.r.t. Tender No. E-215 - 14 items approved as note 1& 2 Letter to dpt. for revised consignee on 20.02.2026 & 05.03.2026 - 04 items L1 Rate is higher than AA Rate- Rs.34,50,663/-; Retender note put up 13.03.2026 - 02 Items No Response Rs.14,73,165/- Retender note put up 13.03.2026
65 | E-257 | 124 | 22/12/2025 | PHD | 2026-05-01 | 40494296 | 30/01/2026 | 2026-12-02 | 2026-03-02 |  | 23/02/2026 | 2026-04-03 | 2026-05-03 | 13/03/2026 | L1 Finalised | PO Awaited | • 12 items for repeat order w.r.t. Tender No. E-215 • 06 Items No Response (Rs. 69,45,180) }; Retender note put up 13.03.2026 • 02 items L1 rate is higher than - AA Rate - Rs.3,86,000/- ; Retender note put up 13.03.2026 • 01 item approved in TAC 05.02.2026; Letter to dpt. for revised consignee on 18.02.2026,13.03.2026 (Rs. 2,64,600/-) ; • 03 items approved in TAC 20.02.2026 Rs.11,54,706/- ; Letter to dpt. for revised consignee on 26.02.2026,13.03.2026
66 | RRT-151 |  | 26/08/2024 | PHD | 26/08/2024 | 11606605 | 2025-10-07 | 21/07/2025 | 15/07/2025 |  | 2025-08-09 | 15/09/2025 | 16/09/2025 | 2025-09-12 | L1 Finalised | PO Awaited | • 21 items for repeat order w.r.t. Tender No. E-215 • Consignee recevied for 13 items on 20.03.2026; PO note put up 23.03.2026 • 04 items L1 Rate is higher than AA Rate - 32,92,436/- ; • 05 Items No Response (Rs. 80,38,518) }
67 | RT-182 |  | 27/12/2023 | PHD | 2024-08-02 | 3091200 | 23/12/2024 | 2025-08-01 | 30/12/2024 |  | 15/01/2025 | 22/01/2025 |  |  | L1 Finalised | PO Awaited | 7 items for repeat order w.r.t. Tender No. E-204/E-207 • Consignee recevied for 1 item on 20.03.2026; PO note put up 23.03.2026 • 06 items No Response (E-204,E-207- Rs. 5,09,90,615/-)
68 | Reserved | Owt No.58719-724 | 20/08/2025 | PHD | 2025-05-12 | 2,86,01,286 | [8 empty] | L1 Finalised | PO Awaited | • TAC Approved Date 23.03.2026; awaited for fund
69 | Reserved | 139 R | 29/08/2025 | PHD | 29/08/2025 | 48,08,500 | [8 empty] | L1 Finalised | PO Awaited | No Response all 04 items ; Retender note put up 13.03.2026
70 | Reserved | 19 | 17/02/2025 | PHD | 2025-12-03 | 56311246 | [8 empty] | L1 Finalised | PO Awaited | • TAC Approved Date 23.03.2026; awaited for Consignee • Letter sent to department Regarding Revised Consignee for HBPCL Items (4 Items) on dt.16.03.2026